## Sheet1
Time Estimation for Alwsey Property Management System
Work To-do | Estimated Days
Admin Theme Preparation | 4
Front-End Theme | 4
Database Design | 12
Framework Setup | 7
Login System | 4.5
Blog Setup | 1
Blog Integration | 2
Total Working Days | 34.5

## Sheet2
Screens for Admin
Serial # | Task | Task Type | Functionalities | Estimated Hours | Questions
1 | Dashboard | Dashboard | 1. Listing | 3 | Pagination required?
|  |  | 2. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 3. Approve/Reject Property | 0.45
2 | Search | Property Management |  | 12
3 | Approved Listing | Property Management | 1. Records per page | 0.5
|  |  | 2. Sorty by type | 1
|  |  | 3. Sort by purpose | 1
|  |  | 4. Search by user name | 2.5 | Will we suggest user name to Admin?
|  |  | 5. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 6. Approve/Reject Property | 0.45
4 | Pending Listing for Approval | Property Management | 1. Records per page | 0.5
|  |  | 2. Sorty by type | 1
|  |  | 3. Sort by purpose | 1
|  |  | 4. Search by user name | 2.5
|  |  | 5. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 6. Approve/Reject Property | 0.45
5 | Rejected Listing | Property Management | 1. Records per page | 0.5
|  |  | 2. Sorty by type | 1
|  |  | 3. Sort by purpose | 1
|  |  | 4. Search by user name | 2.5
|  |  | 5. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 6. Approve/Reject Property | 0.45
6 | My Profile | My Account | 1. Country list | 0.5
|  |  | 2. Upload image | 45
7 | Change Password | My Account |  | 3
8 | User Roles for Approval | My Account | 1. Listing | 3.5
|  |  | 2. Approve/Reject Role | 0.45
9 | Approved User | My Account | 1. Records per page | 0.5
|  |  | 2. Search by user name | 2.5
|  |  | 3. View User | 0.15 | View user on front-end?
|  |  | 4. Edit User | 5
|  |  | 5. Reject User | 0.5
|  |  | 6. Delete User | 0.5
10 | Pending User | My Account | 1. Records per page | 0.5
|  |  | 2. Search by user name | 2.5
|  |  | 3. View User | 0.15 | View user on front-end?
|  |  | 4. Edit User | 5
|  |  | 5. Reject User | 0.5
|  |  | 6. Delete User | 0.5
11 | Rejected User | My Account | 1. Records per page | 0.5
|  |  | 2. Search by user name | 2.5
|  |  | 3. View User | 0.15 | View user on front-end?
|  |  | 4. Edit User | 5
|  |  | 5. Reject User | 0.5
|  |  | 6. Delete User | 0.5
12 | User Profile | My Account | 1. Update User | 2
|  |  | 2. View User | 0.5
|  |  | 3. Deleted User | 1 | View user on front-end?
|  |  | 4. Reject/Approve | 5
13 | Add Advertisement | Tools | 1. Upload image | 1.5 | Time will increase in-case of more advertisement
14 | All Advertisement | Tools | 1. View Advertisement | 0.5 | View advertisement on front-end?
|  |  | 2. Edit Advertisement | 2
|  |  | 3. Reject Advertisement | 0.45
|  |  | 4. Delete Advertisement | 1
15 | All Email Alert | Tools | 1. Records per page | 0.5
|  |  | 2. Search by user name | 2.5
|  |  | 3. View Email | 4 | View screen mock-up is missing
|  |  | 6. Delete Email | 0.45

## Sheet3
Screens for User
Serial # | Task | Task Type | Functionalities | Estimated Hours | Questions
1 | Dashboard | Dashboard | 1. Property Performance Chart
|  |  | 2. Recent Listing | 3
|  |  | 3. Edit property | 6
|  |  | 3. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 4. Delete Property | 1
2 | Search | Property Management |  | 12
3 | Add New Property | Property Management | 1. Quick Submission | 5
|  |  | 2. Upload Property Images | 3
|  |  | 3. Add new client | 5
|  |  | 4. Choose from existing client | 2
3 | Add New Property | Property Management | 1. Advance Submission | 5
|  |  | 2. Upload Property Images | 3
|  |  | 3. Add new client | 5
|  |  | 4. Choose from existing client | 2
|  |  | 5. Floorplans | 4
|  |  | 6. Documents |  | No Detail
|  |  | 7. Videos |  | No Detail
|  |  | 8. Status | 2
4 | Active Property Listing For Sale | Property Management | FOR SALE
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
5 | Active Property Listing For Rent | Property Management | FOR RENT
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
6 | Active Property Listing For Wanted | Property Management | FOR WANTED
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
7 | Pending Property Listing For Sale | Property Management | FOR SALE
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
8 | Pending Property Listing For Rent | Property Management | FOR RENT
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
9 | Pending Property Listing For Wanted | Property Management | FOR WANTED
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
10 | Rejected Property Listing For Sale | Property Management | FOR SALE
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
11 | Rejected Property Listing For Rent | Property Management | FOR RENT
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
12 | Rejected Property Listing For Wanted | Property Management | FOR WANTED
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
13 | Expired Property Listing For Sale | Property Management | FOR SALE
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
14 | Expired Property Listing For Rent | Property Management | FOR RENT
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
15 | Expired Property Listing For Wanted | Property Management | FOR WANTED
|  |  | 1. Records Per Page | 0.5
|  |  | 2. Sort By | 0.5
|  |  | 3. Order By | 0.5
|  |  | 4. Listing | 2
|  |  | 5. Edit property | 6
|  |  | 6. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 7. Delete Property | 1
16 | My Profile | My Account | 1. Country list | 0.5
|  |  | 2. Upload image | 45
17 | User Role | My Account |  | 4
18 | General Settings | My Account |  | 2.5
19 | Change Password | My Account |  | 3
20 | Traffic Summary | Report
21 | Property Views | Report
22 | Property Visits | Report
23 | CTR | Report
24 | Traffic By Location | Report
25 | Listing Summary | Report | by Day
26 | Listing Summary | Report | by Date
27 | Listing Summary | Report | by Location
28 | Listing Summary | Report | by Performance
29 | Favourites | Tools | 1. Listings of Property | 2
|  |  | 2. Edit Property | 6
|  |  | 3. View Property Detail | 0.15 | View means view property on front-end?
|  |  | 4. Delete Property | 1
30 | Create Alert | Tools |  | 7
31 | All Email Alert | Tools | 1. Records per page | 0.5
|  |  | 2. Search by user name | 2.5
|  |  | 3. View Email | 4 | View screen mock-up is missing
|  |  | 6. Delete Email | 0.45

## Sheet4
Admin Theme
Serial # | Task | Task Type | Estimated Hours | Questions
1 | Dashboard | Dashboard | 2
2 | Search | Property Management | 1
3 | Approved Listing | Property Management | 1
4 | Pending Listing for Approval | Property Management | 1
5 | Rejected Listing | Property Management | 1
6 | My Profile | My Account | 1
7 | Change Password | My Account | 0.5
8 | User Roles for Approval | My Account | 0.5
9 | Approved User | My Account | 1
10 | Pending User | My Account | 0.5
11 | Rejected User | My Account | 0.5
12 | User Profile | My Account | 0.5
13 | Add Advertisement | Tools | 1
14 | All Advertisement | Tools | 1.5
15 | All Email Alert | Tools | 1.5
|  | Total | 14.5
User Theme
1 | Dashboard | Dashboard | 2
2 | Search | Property Management | 1
3 | Add New Property | Property Management | 1.5
4 | Add New Property | Property Management | 1.5
5 | Active Property Listing | Property Management | 1
6 | Pending Property Listing | Property Management | 1
7 | Rejected Property Listing | Property Management | 1
8 | Expired Property Listing | Property Management | 1
9 | My Profile | My Account | 0.5
10 | User Role | My Account | 0.5
11 | General Settings | My Account | 0.5
12 | Change Password | My Account | 0.5
13 | Traffic Summary | Report | 1
14 | Property Views | Report | 1
15 | Property Visits | Report | 1
16 | CTR | Report | 2
17 | Traffic By Location | Report | 2
18 | Listing Summary | Report | 1
19 | Listing Summary | Report | 1
20 | Listing Summary | Report | 1
21 | Listing Summary | Report
22 | Favourites | Tools | 0.5
23 | Create Alert | Tools | 1
24 | All Email Alert | Tools | 0.5
|  | Total | 24

## Sheet5
Front End Theme
Serial # | Task | Task Type | Estimated Hours | Questions
1 | index |  | 5
2 | search result |  | 3
3 | all properties |  | 4
4 | categories |  | 3
5 | single property page |  | 2
6 | addproperty |  | 2
7 | user profile |  | 3
8 | About |  | 1
9 | blog |  | 3
10 | blog single |  | 2
11 | contact |  | 2
12 | Login |  | 1
13 | Registration |  | 1
| Total |  | 32